## Overview
BUDGET REPORT
PROJECT NAME | Main Street Improvements Project
Captial Facilities Plan # | RD-101 | Captial Facilities Plan # | 18013
|  |  | Total Budget: | 3820000
|  |  | Budget utilized | 3065164.5087
|  |  | Budget Remaining | 754835.4913
BUDGET
Budget Source | Budget Code/Alias | Budget Amount | Utilized | Remaining
FHWA Grant | 301-000-333-20-20-50 | 3304300 |  | 3304300
TIZ 1 | 301-016-595-30-60-05 | 335000 |  | 335000
TBP (removed) |  |  |  | 0
R2 Main | 304-016-595-30-60-05 | 3485000 |  | 3485000
DESIGN CONTRACT | contract expires: | 2025-12-31 | Contract Remaining | 156224.44
Prime Consultant: | Transpo Group |  | Total Design Contract | 418177
Project Manager: | Kristen Cassias
Council Authorization Date: | 2022-12-13
Contract/Award Date: | 2022-12-15 | 18013_Transpo_PSA_221215 - signed | Amount | 350000
Supplement 1 | 2023-03-16 | 18013_PSA Supplement 1_230315_Rev1 - signed.pdf | Amount | 68177
Supplement 2 | 2024-11-26 | 18013_PSA Supplement 2_241126 - signed.pdf
ROW ACQUISITION |  | status | Total Cost | 76485
DeYoung Family Trust | TCE | acquired |  | 3045
Lakeview Flats LLC | TCE | acquired |  | 3440
Lake Mall LLC | TCE & ROW | acquired |  | 17700
Norman, Leon & Jennifer | TCE & ROW | acquired |  | 15100
First Baptist Church of LS | TCE & ROW | acquired |  | 37200
CONSTRUCTION CONTRACT |  |  | Contract Remaining
Advertisement Date | 2024-09-13 |  | Contract Total | 3076521.71
Bid Opening | 2024-10-15 |  | Contract Paid-to-date: | 2500507.6787
Council Authorization Date: | 2024-11-26
Contract/Award Date | 2024-12-10 | 18013_Public Works Contract_241122-signed.pdf
PreContruction Meeting Date | 2025-01-07
Notice to Proceed Date | 2025-01-25 | 2025-02-28
Working Days | 95 | Begin - 3/4/2025

## Design
Design Contract
| Transpo Group |  |  |  | Contract total | 418677
| Kristen Cassias |  |  |  | Contract utilized | 262452.56 | 62.69%
[5 empty] | Contract Remaining | 156224.44 | 37.31%
INVOICES
| invoice # | Invoice Date | total
2023 | 30110 | 2023-04-06 | 33084.6
| 30267 | 2023-05-03 | 9245.14
| 30442 | 2023-06-07 | 1404.52
| 30648 | 2023-07-05 | 8045.44
| 30820 | 2023-08-02 | 2183.92
| 30992 | 2023-09-06 | 7333.76
| 31210 | 2023-10-04 | 18949.79 |  |  |  |  | 6000
| 31368 | 2023-11-01 | 16079.97 | 2023 Total
| 31624 | 2023-12-08 | 26298.79 | 122625.93
2024 | 31785 | 2024-01-03 | 58249.98
| 31978 | 2024-02-07 | 8691.95
| 32175 | 2024-03-07 | 34139.52
| 32457 | 2024-04-19 | 12051.36
| 32741 | 2024-06-06 | 13193.33
| 32960 | 2024-07-03 | 6068.46
| 33171 | 2024-08-08 | 2228.77
2025 | 34415 | 2025-03-05 | 1805.88
| 34695 | 2025-04-02 | 1650.38
| 35141 | 2025-06-04 | 1245.69
| 35578 | 2025-08-06 | 501.31
|  | Total | 262452.56

## ROW
ROW Acquisition
DCI Engineers (subconsultant of Transpo Group) |  |  |  | Contract total | 418677
Roxanne Grimm |  |  |  | Contract utilized | 0 | 0%
|  |  |  | Contract Remaining | 418677 | 100%
Parcel # | Owner: | Address:
553800000600 | City of Lake Stevens
553800000700 | City of Lake Stevens
553800000701 | City of Lake Stevens
29060800411300 | City of Lake Stevens
553800003300 | First Baptist Church - Lake Stevens | 1702 Main Street
29060800412900 | Lake Mall LLC | 1803 Main Street
29060800403700 | Leon Norman | 1705 125th St. NE
City Owned Property Recording
Harmsen On-Call | HARMSEN-Task Order 2023-01_signed.pdf |  | Contract total | 7000
|  |  | Utilization | 6587.2 | 94.1%
INVOICES |  |  | Remaining | 412.8 | 5.897%
invoice # | Invoice Date | total
23_1742 | 2023-12-20 | 6307.2
24_0032 | 2024-01-22 | 280
| Total | 6587.2

## CM Services
Construction Management Services
KBA, Inc. |  |  | Contract total | 411861
Micael Serrano |  |  | Contract utilized | 295617.07 | 71.78%
|  |  | Contract Remaining | 116243.93 | 28.22%
Scope and Fee: | 1a. Main Street Improvements - KBA Estimated Budget Rev. 3.pdf |  | DBE Billed |  | 0% | DBE Goal
Contract: | 4. LP_AEPS-NegotiatedHourlyRate_Draft_250109.pdf
INVOICES
invoice # | Invoice Date | total
3009325 | 2025-02-21 | 9133.26
3009354 | 2025-03-07 | 25927.3
3009480 | 2025-04-24 | 39642.85
3009540 | 2025-05-14 | 42837.29
3009599 | 2025-06-10 | 48152.22
3009663 | 2025-07-10 | 63329.74
3009759 | 2025-08-12 | 66594.41
| Total | 295617.07

## Construction
Refer to Project Tracking Spreadsheet