## Budget Worksheet
36th St Bridge
PROJECT FUNDING
SOURCE | 2025 | 2026 | TOTAL
(Local) | 1131000 | 0 | 1131000
Future (Source(s) | 0 | 0 | 0
Total | 1131000 | 0 | 1131000
PROJECT WORKING EXPENSE BUDGET
PLANNING/DESIGN/ENG EXPENSES
| PROJECTED EXPENSE | PAID TO DATE | BALANCE REMAINING | % SPENT OUT | % SCOPE COMPLETED | NOTES
DESIGN (David Evans) | 1121071.48 | 76569.37 | 1044502.11 | 6.83% | 85%
INSPECTOR-MATERIAL (TBD) | #REF! | #REF! | #REF! | #REF! | #REF!
PERMITTING & AGENCY | 0 | #REF! | #REF! | #REF! | 0%
MISC EXPENSES | 0 | #REF! | #REF! | #REF! | 0%
SUBTOTAL | #REF! | #REF! | #REF! | #REF!
|  | (Over)/Under Design Budget | #REF!
CONSTRUCTION EXPENSES
| PROJECTED EXPENSE | PAID TO DATE | BALANCE REMAINING | % SPENT OUT | % SCOPE COMPLETED | NOTES
CONTRACTOR (TBD) | 20000 | 0 | 20000 | 0% | #REF!
CONTINGENCY | 0 | 0 | 0 | 0% | 0%
SUBTOTAL | 20000 | 0 | 20000 | 0%
|  | (Over)/Under Construction Budget | 0
|  | OVERALL PROJECT BUDGET STATUS (Over)/Under | #REF!
#REF!

## DEa
36th St Bridge
Project Engineer: Ben Romanaggi
Vendor: | DEA
Account #
[8 empty] | Original Contract (Preliminary Design Phase) | 1121071.48
[8 empty] | Future Supplement | 0
[8 empty] | Total Contract (Authorized to Date) | 1121071.48
PP # | Inv # |  | Date of Inv. | Work Thru | Funding Distribution |  |  |  | Amount
[5 empty] | See Above | Not Used | Not Used | Not Used
PP#1 | 592119 |  | 2025-06-16 | 2025-05-31 | 12363.39 | 0 |  |  | 12363.39
PP#2 | 594648 |  | 2025-07-10 | 2025-06-28 | 14319.73 | 0 |  |  | 14319.73
PP#4 | 2024026.0000-1 | Perteet | 2025-07-08 | 2025-06-29 | 7062.03 | 0 |  |  | 7062.03
PP#3 | 596821 | DEA | 2025-08-14 | 2025-08-02 | 21582.24 | 0 |  |  | 21582.24
PP#4 | 2024026.0000-2 | Perteet | 2025-08-11 | 2025-08-03 | 8516.31 | 0 |  |  | 8516.31
PP#5 | 2025-172 | Cultural Resources | 2025-07-09 | 2025-07-09 | 172.56 | 0 |  |  | 172.56
PP#6 | 599518 | DEA | 2025-09-12 | 2025-08-30 | 12553.11 | 0 |  |  | 12553.11
PP#8 | [5 empty] | 0 |  |  | 0
PP#9 | [5 empty] | 0 |  |  | 0
PP#10 | [5 empty] | 0 |  |  | 0
PP#11 | [5 empty] | 0 |  |  | 0
PP#12 | [5 empty] | 0 |  |  | 0
PP#13 | [5 empty] | 0 |  |  | 0
PP#14 | [5 empty] | 0 |  |  | 0
PP#15 | [5 empty] | 0 |  |  | 0
PP#16 | [5 empty] | 0 |  |  | 0
PP#17 | [5 empty] | 0 |  |  | 0
PP#18 | [5 empty] | 0 |  |  | 0
PP#19 | [5 empty] | 0 |  |  | 0
PP#20 | [5 empty] | 0 |  |  | 0
PP#21 | [5 empty] | 0 |  |  | 0
PP#22 | [5 empty] | 0 |  |  | 0
|  |  |  | Sums To Date: | 76569.37 | 0 |  | 0 | 76569.37
[8 empty] | Total Payments | 76569.37
[8 empty] | Total Remaining Balance: | 1044502.11
[8 empty] | % of Contract Complete: | 6.83%
[8 empty] | % of Work Scope Complete: | 8%

## Breakdown by task
Billing Alias | SWCCC
Budget (2025 adopted) | 1353000
Contract Amount | 1121071.48
PWB Loan | 911000
Contract Expiration Date | 2026-12-31
Task | Description | Consultant | Deliverable | Cost Estimate | Target | Notes | Spent To Date | Remaining | % Complete | % Complete of Target | INV 592119 | INV 594648 | INV 596821 | INV 599518 | INV 601771 | INV 604552 | INV 606639 | INV 608413 | INV 610643
1 | Project management | DEA |  | 93279.03 | 60000 | Reduce bi-weekly meetings with city and design team and move to meeting that are for milestones and critical paths | 19330.51 | 73948.52 | 20.72% | 32.22% | 970.08 | 1592.44 | 3229.91 | 1873.09 | 1208.72 | 2315.36 | 1908.88 | 2388.82 | 3843.21
1.1 | Kickoff Meeting |  |  | 10367.8
1.2 | Bi-weekly meeting with City |  |  | 22732.36
1.3 | Invoicing and Monthly Reports |  |  | 19091.33
1.4 | Coordination with Perteet for Stormwater |  |  | 4896.45
1.5 | Bi-weekly meeting with design team |  |  | 19699.21
1.6 | Design team management - 5 subs |  |  | 8966.12
1.7 | Schedule Creation and Maintenance |  |  | 5123.5
1.8 | Communications Plan |  |  | 1121.39
1.9 | QAQC Coordination |  |  | 1280.87
2 | Data Gap Analysis Detail |  |  | 35193.04 | 35193.04 |  | 14134.79 | 21058.25 | 40.16% | 40.16% | [5 empty] | 14134.79
2.1 | Project management - Gap Analysis | Herrera |  | 24834.34
2.2 | Data Gap Analysis Detail | Herrera | 2-page bulleted list of data gaps | 10358.7
3 | Survey | DEA | CAD files, 4 legal descriptions/exhibit packets | 10808.67 | 10808.67 |  | 5299.5 | 5509.17 | 49.03% | 49.03% |  | 2627.37 |  | 455.7 | 773.38 | 911.4 | 531.65
4 | Geotechnical | Geosyntec | Geotechnical report to include with PS&E | 19991 | 19991 |  | 1112.5 | 18878.5 | 5.565% | 5.565% |  |  |  | 1112.5
5 | Hydraulic Analysis and Restoration Design |  |  | 147859.34 | 73929.67 |  | 18519.45 | 129339.89 | 12.53% | 25.05% |  | 7 |  |  |  | 2638.95 |  | 15873.5
5.1 and 5.2 | Hydraulic Analysis and Restoration Design | Herrera | • Emailed model results screen shots showing proposed conditions flow depths and velocities corresponding to the design developed for the 30% Design Package listed in Task 5.2.1. • Draft 60% Hydraulic and Restoration Design Memorandum in pdf and Word format, including draft scour analysis and hydraulic design calculations, to be submitted with the 60% Design Package listed in Task 5.2.2. • Final 90% Hydraulic and Restoration Design Memorandum in pdf format, including final scour analysis and hydraulic design calculations, to be submitted with the 90% Design Package listed in Task 5.2.3. • Four design submittals: 30%, 60%, 90% Draft Final, Final 100% Bid Ready • Habitat Restoration Design plans to be prepared by Herrera will include up to 12 sheets as indicated in the table at the end of this Scope of Work.
5.2.1 | 30% Restoration Design | Herrera | • Drawing plan sets will be on 11”x17” (half-size) electronic .pdf (Adobe) file format. • Cost estimate in bid tab format, in Microsoft Excel electronic file format. • Draft construction contract document content in electronic .docx (Microsoft Word) file format, including special provisions in Divisions 2 through 9. • Draft engineer’s opinion of construction cost estimate in bid tab format in electronic .xlsx (Microsoft Excel) file format.
5.2.2 | 60% Restoration Desing | Herrera | • Drawing plan sets will be on 11”x17” (half-size) electronic .pdf (Adobe) file format. • Spec list identifying anticipated special provision specification sections and measurement and payment for bid items to be developed by Herrera in further design deliverables; the list of anticipated special provisions will be provided in either electronic MS Word or MS Excel file format. • Cost estimate for Herrera’s design items in bid tab format, in Microsoft Excel electronic file format.
5.2.3 | 90% Final Draft Restoration Design | Herrera | • 1 copy of Herrera's drawings on 11"x17" (half-size) electronic .pdf (Adobe) file format. • 1 copy of Herrera's drawings in 22"x34" (full size) electronic .pdf (Adobe) file format. • Draft of special provisions in Divisions 2 through 9 in electronic .docx (Microsoft Word) file format. • Draft opinion of construction cost estimate in bid tab format in electronic .xlsx (Microsoft Excel) file engineer’s format.
5.2.4 | Final 100% (Bid Ready) Restoration Design | Herrera | Signed and stamped design plans in 11"x17" (half size) electronic .pdf (Adobe) file format. • Signed and stamped design plans in 22"x34" (full size) electronic .pdf (Adobe) file format. • Technical special provisions for construction stamped and signed by a professional engineer licensed in the State of Washington in electronic .pdf (Adobe) file format. • All special provisions in electronic .docx (Microsoft Word) file format. • Final engineer's opinion of construction cost estimate in Microsoft Excel electronic file format. • Complete copy of electronic drawing files in AutoCAD and Civil 3D file formats.
6 | Environmental Permitting | Herrera |  | 45411.53 | 45411.53 |  | 577.1 | 44834.43 | 1.271% | 1.271% | [7 empty] | 577.1
6.1 | Enviro Permitting - Agency Coordination - Pre-Application Meeting | Herrera
6.2 | Enviro Permitting - SEPA Checklist | Herrera
6.3 | Enviro Permitting - JARPA | Herrera
6.4 | Enviro Permitting - HPA | Herrera
6.5 | Enviro Permitting - USACE 404 | Herrera
6.6 | Enviro Permitting - Section 7 - ESA | Herrera
6.7 | Enviro Permitting - Critical Area Assessment | Herrera
6.8 | Enviro Permitting - Ecology Section 401 | Herrera
6.9 | Enviro Permitting - Post-permit application support and coordination | Herrera | • All draft deliverables will be prepared in electronic file format (MS Word) to allow for tracked changes by project reviewers. Final deliverables will incorporate one consolidated set of review comments/revisions and will be submitted in pdf file format. • Draft and final pre-application meeting agenda and meeting minutes • Draft and final JARPA form and site plan figures • Draft and final ESA compliance documentation • HPA application information for upload to APPS • Draft and final City of Lake Stevens Critical Areas Assessment and Mitigation Plan report • Draft and Final Section 401 Water Quality Certification Notifications
7 | Cultural Resources | Cultural Resources Consultant | • One Draft and Final Cultural Resources Assessment Report (with Site Forms, if completed), provided electronically | 5493 | 5493 |  | 172.56 | 5320.44 | 3.141% | 3.141% |  |  | 172.56
8 | ROW Acquisition Project Management |  |  | 58866.65 | 10000 | The City will manage ROW acquisition, deliverable = legal exibits | 6.3 | 58860.35 | 0.0107% | 0.063% |  | 6.3
8.1 | ROW Acquisition Project Management | Commonstreet
8.2 | Title Review and Conveyance Documents | Commonstreet
8.3 | Appraisal and Appraisal Review Coordination | Commonstreet
8.4 | Negotiations, Administrative Settlements, QA/QC | Commonstreet
9 | Utility Coordination | DEA | Incorporation of utility work requirements in plans and specifications. Any relocation work will be reflected as “by others.” | 6400.66 | 6400.66 |  | 0 | 6400.66 | 0% | 0%
10 | Roadway Civil Design | Perteet |  | 237317.11 | 118658.555 |  | 49468.01 | 187849.1 | 20.84% |  |  |  | 8516.31 | 1768.17 | 746.19 | 777.05 |  | 884.62 | 36775.67
10.1 | Roadway Civil Design - 30% | Perteet | • Electronic copy of the 30% plan set in PDF format via email or SharePoint • Electronic copy of the 30% opinion of cost summary submitted in PDF format via email or SharePoint.
10.2 | Roadway Civil Design - 60% | Perteet | • Electronic copy of the 60% plan set in PDF format via e-mail or SharePoint • Electronic copy of the 60% opinion of cost summary submitted in PDF format via email or Sharepoint • Electronic copy of the 60% special provisions and applicable GSPs with fill ins for the civil design elements in Microsoft Word format via e-mail or SharePoint
10.3 | Roadway Civil Design - 90% | Perteet | • Written responses to 60% civil comments (PDF) • Electronic copy of the 90% plan set in PDF format via e-mail or SharePoint • Electronic copy of the 90% opinion of cost summary submitted in PDF format via e-mail or Sharepoint
10.4 | Roadway Civil Design - 100% bid ready | Perteet | • Written responses to 90% comments • Electronic copy of the final plans; half size and full size signed plans, in PDF format via email or SharePoint • Electronic copy of the opinion of cost summary submitted in PDF format via electronic email or SharePoint • Electronic copy of the 100% civil special provisions submitted in PDF format via electronic e-mail or SharePoint • Bidding support or construction engineering services are excluded.
10.4 | Perteet Project Management | Perteet | Progress reports and coordination with DEA
11 | Community Engagement | DEA |  | 4408.74 | 0 | The City will manage community engagement | 0 | 4408.74 | 0%
11.1 | Outreach Materials | DEA | Requested materials
11.2 | Public Meeting Attendance | DEA | • Attendance at the meeting will include one member from the design team and the project manager. • Mileage will be charged at Federal rates.
12 | Stormwater Design | DEA |  | 67209.42 | 40325.652 | Assumption: MR 1 - 9 but no flow control | 629.28 | 66580.14 | 0.9363% | 1.56% |  |  | 116.74 | [5 empty] | 512.54
12.1 | Stormwater - 30% | DEA | • 30% design-level plans (half-size [11”x17”], PDF) • 30% design-level opinion of cost summary (Excel)
12.2 | Stormwater - 60% | DEA | • Written responses to 30% comments • 60% design-level plans (half-size [11”x17”], PDF) • 60% design-level opinion of cost summary (Excel)
12.3 | Stormwater - 90% | DEA | • Written responses to 60% comments • 90% design-level plans (half-size [11”x17”], PDF) • 90% design-level opinion of cost summary (Excel) • 90% design-level specifications (run-list and individual specifications files, Word)
12.4 | Stormwater - 100% bid ready | DEA | • Written responses to 90% comments • 100% design-level plans (half-size [11”x17”], PDF) • 100% design-level opinion of cost summary (Excel) • 100% design-level specifications (run-list and individual specifications files, Word)
12.4 | Stormwater Report | DEA | • Draft Stormwater Report (PDF Electronic file). Submitted with 30% design. • Final Draft Stormwater Report (PDF Electronic file). Submitted with 60% design. • Comment responses from 30% submittal
13 | Structural Design | DEA |  | 367016.03 | 220209.618 | Assumption - bridge design is a standard bridge | 141090.36 | 225925.67 | 38.44% | 64.07% | 11393.31 | 10086.62 | 9546.72 | 7343.65 | 16382.65 | 12291.54 | 5517.04 | 8211.19 | 60317.64
13.1 | Structural - 30% | DEA | • Bridge type alternatives memo. • 30% design-level plans (half-size [11x17], PDF). • 30% design-level opinion of cost Summary (Excel).
13.2 | Structural - 60% | DEA | • Written responses to 30% comments. • 60% design-level plans (half-size [11x17], PDF) • 60% design-level opinion of cost summary (Excel) • Preliminary Specification Manual (Word)
13.3 | Structural - 90% | DEA | • Two 11x17 (half size) copies of Plans • Two copies of the 90% Specifications Manual • Two copies of the quantity Estimates and opinion of construction cost.
13.4 | Structural - 100% bid ready | DEA | • Written responses to 90% comments. • 100% design-level plans (half-size [11x17], PDF) • 100% Specifications Manual (Word) • 100% quantity Estimates and opinion of construction cost (Excel).
14 | QAQC | DEA |  | 21817.33 | 10908.665 |  | 0 | 21817.33 | 0% | 0%
14.1 | QAQC - Constructability Review | DEA | • Constructability Review comments for PS&E packages at 60% and 90% design levels. • Construction schedule at 60% and 100% levels. • Construction estimation for PS&E packages at 60%, 90%, & 100% design levels.
14.2 | QAQC Construction CPM Schedule | DEA
14.3 | QAQC Construction Estimation | DEA
15 | OPTION - Construction Phase Support | DEA
Total |  |  |  | 1121071.55 | 657330.06 |  | 250340.36 | 870731.19 | 22.33% | 38.08% | 12363.39 | 14319.73 | 21582.24 | 12553.11 | 19110.94 | 33069.09 | 7957.57 | 27935.23 | 101449.06 | 0 | 0
[11 empty] | November 2025 - Reimbursement Request |  |  |  |  | January 2026 - Reimbursement Request

## Loan Reimbursements
Date of Reimbursement Request | Total Reimbursement Amount
2025-11-21 | 79929.41