## 2025 GANNT
City of Lake Stevens
2025 Capital Improvement Projects
Project type. | CFP No. | Project # | Project Name | Status | Scope status | Schedule Status | Budget Status | 2024 | 2025 | [11 empty] | 2026 | Project Charter (add link) |  |  |  | Pre-app Done | Total Project Cost
[8 empty] | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Executed | Draft | Not Started | N/A
ERIK
ST | TBD-02/03 | 23010 | 91st Ave SE Sidewalk (4th to Market) & (8th to 4th St SE) | Final Payments and closeout |  |  |  | Close | [13 empty] | Yes |  |  |  | Yes | 1690000
PA | PR-107 | 20002 | Lake Stevens Bayview Connector Phase 0 | 2 weeks to finish, Trail Final Paving this week |  |  |  | CN | Close | [12 empty] | Yes |  |  |  | Yes | 1050000
PA | PR-108 | 240010 | Lake Stevens Bayview Connector Phase 0.5 | Working with Consultant to scope and finalize Design |  |  |  | Design | Design | Design | ROW | Design | Design | Design | Design | Design | Ad | CN | Close |  |  |  | 23006_Project Charter_230502.docx |  |  | No | 800000
PA | PR-100 | 23016 | Frontier Heights Phase II | Finalizing Design/Permits. Preparing Advertisement |  |  |  | Design | Design | Design | Design | Design | Design | Design | Ad | Ad | Ad | Ad | CN | CN | Close |  | 22016_Project Charter_231107.docx |  |  | Yes | 2400000
ST | RD-101 | 18012 | Main St. Improvements (16th St NE to 20th St NE) | Awarded Contract, CM Services Award, Construction Begins 2025 |  | Impeded |  | AD | Hold | Hold | CN | CN | CN | CN | CN | CN | Hold | Hold | CN | Close |  |  |  |  | X | Yes | 4040000
ST | FC-112 | 23006 | 131st Avenue Infrastructure Improvements | Finalizing ROW/Design/Permits. Preparing Advertisement |  | Impeded |  | Design | ROW | Design | Design | Design | Design | ROW | ROW | ROW | Ad | CN | CN | CN | CN |  | 23006_Project Charter_230502.docx |  |  | Yes | 2800000
FA | FC-114 |  | Machias Sewer Infrastructure Improvements |  |  |  |  | Design | Design | Design | Design | Design | Design | Design | Ad | [10 empty] | No | 3300000
FA | FC-111 | [24 empty] | ? | 30000
FA | FC-111 | [24 empty] | ? | 30000
ST | RD-203 |  | Annual Pavement Preservation Program & Citywide Striping | Substantially Complete | [5 empty] | Planning | Design | Design | Design | AD | CN | CN | Close | [9 empty] | 900000
SW |  |  | Downtown Regional Stormwater Facility | Pre-app meeting mid-July | Stopped | Stopped | Stopped | Hold: Planning; CN: Design; CN: Design; CN: Design; CN: Design; CN: Design; CN: Close | [6 empty] | 500000
ST | TBD-04 |  | 117th Ave NE Sidewalk (20th to 26th St NE) | Design Starting |  |  |  | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | [6 empty] | 1808000
ST | TBD-07 |  | Soper Hill Sidewalk (Lake Drive to SR9) | Project Charter |  |  |  | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Design | Design | Design | Design | Design | [6 empty] | 3700000
ST |  |  | 91st SE Phase 2 Multiuse Path (TBP 5) | Accepting Grant. Consultant Selection | [8 empty] | Planning | Planning | Design | Design | Design | Design | Design | Design | [6 empty] | 3100000
ST | TBD-07 |  | 99th Ave Sidewalk (TBP 14) | Construction begins mid July | [5 empty] | Design | Design | Design | Design | AD | CN | CN | Close
SW | SW-104 |  | Bridge 06 Replacement - 36th Street NE | Project Charter, Design Starting |  |  |  | Planning | Planning | Planning | Planning | Planning | Design | Design | Design | Design | Design | Design | Design | Design | [6 empty] | 6661000
ST | RD-113 |  | 20th St NE and Main Street Roundabout | 60% PS&E by July |  |  |  | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | [5 empty] | Yes | 2700000
WHITNEY
ST |  |  | Annual Citywide Road Striping and Thermoplastic | Included in 2025 Overlay contract, out to ad now |  |  |  | Planning | Design | Design | Design | Design | Design | AD | CN | CN | Close | [8 empty] | N/A | 100000
ST | RD-205 |  | Traffic Safety & Calming Program | Scope work: Cameras project (AH), Traffic Calming Policy (LSMC) and Program (including EDDS) development/update |  |  |  | Planning | Planning | Planning | Design | Design | Design | Design | Design | [10 empty] | N/A | 650000
ST |  |  | EDDS Update | Ch. 2 underway |  |  |  | Planning | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | Design | [5 empty] | N/A | 100000
ST |  |  | Mill Spur Public Safety Concerns | Scoping with traffic engineer, evaluating countermeasures |  |  |  | CN: Design; CN: Design; CN: Design |  |  | https://lakestevens.sharepoint.com/:w:/r/teams/CityofLakeStevens/Shared%20Documents/General/08-Public%20Works%20-%20Public/Mill%20Spur/20250703_Charter_MillSpurTrafficCalming.docx?d=w2c58a3d455fb42a5966cd1ea0e6c3e51&csf=1&web=1&e=c9U3lM
SHANNON
SW | SW-106 |  | Hartford Crossing - New and Channel realignment | SoQ Evaluation |  |  |  | grant application | Funding/Granting | Funding/Granting | Funding/Granting | Funding/Granting | Funding/Granting | Design | Design | Design | Design | Design | Design | Design | [6 empty] | 10600000
SW | SW-111 |  | Catherine Creek/Hartford Crossing Replacement | SOQ evaluation |  |  |  | grant application | Funding/Granting | Funding/Granting | Funding/Granting | Funding/Granting | Funding/Granting | Design | Design | Design | Design | Design | Design | Design | [6 empty] | 3400000
AARON
FA | FC-111 |  | PW/Parks Building Feasibility Study | consultant selected | [22 empty] | 30000
ST | RD-205 |  | Traffic Safety Camera Program | bringing to council June
PARKS
PA | PR-206 |  | Eagle Ridge Property Acquisition | Complete |  |  |  | AD: Planning; Hold: Planning; Hold: Close | [6 empty] | 935000
PA |  |  | Feasibility for Eagle Ridge | Stopped | Stopped | Stopped | Stopped | Hold: Planning; CN: Planning; CN: AD
PA | PR-123 |  | Eagle Ridge Storage Building | Bars on windows have been completed. Remaining work will be reported by field this week. (9/2) |  |  |  | CN: Planning; CN: Planning; CN: Planning; CN: CN; CN: CN; CN: CN | [6 empty] | 25000
PA | PR-201 |  | N Cove Marina & Marine Unit Relocation Feasibility | RFQ closes November 19 |  |  |  | AD: Planning; Close: Design | Design | [5 empty] | 4125000
PA | PR-141 |  | North Cove Non-Motorized Dock | Complete |  |  |  | Hold: Permits; Hold: Permits; CN: Permits; Hold: CN; Hold: CN; CN: Close | [5 empty] | Yes | 170000
PA | PR-103 |  | North Cove Light Bollard Replacement | Complete |  |  |  |  | Planning | Planning | Planning | AD |  |  | CN | CN | CN | Close | [8 empty] | 150000
PA | PR-104 |  | Cedarwood Property | Consultant negotiations |  |  |  |  | Planning | Planning | Planning | Select Contractor |  |  | Design | Design | Design | Design | Design | Design | [6 empty] | 1650000
PA | PR-113 |  | Davies Beach Pier Resurfacing | Structural analysis complete, preliminary comments indicate there is minimal work that needs to be done to piles |  | Stopped | Stopped | CN: Planning; CN: Planning; CN: Planning; CN: Design; Hold: Pause | [6 empty] | 100000
PA | PR-106 |  | West Lake Park Recreation Amenities | SCL is amenable to a pump track in this location. |  |  |  | CN: Planning; Hold: Planning; Hold: Planning; CN: Planning; Close: Planning | Design | [5 empty] | 100000
PA | PR-203 |  | Lake Stevens Bayview Connector Phase 1 | Consultant PSA executed, kick off meeting 10/8 |  |  |  | Hold: Planning; Hold: Submit; CN: Consultant selection; Hold: Planning; Hold: Planning; CN: Planning; Close: Planning | Planning |  | Yes |  |  |  | 2700000
PA | PR-102 |  | Eagle Ridge Park Phase II | Consultant selection will begin by Dec | Impeded | Impeded |  | Pause | Pause | Pause | Pause | Pause | Pause | Pause | Pause | Pause | Pause | Restart | Planning | Planning | Planning | Yes |  |  |  | Yes | 3459000
CURTIS
FA |  |  | Evergreen Office Building (siding, HVAC, fire alarm) | RFQ posted, Ratings 3/4, Proceed |  |  |  | CN: Design; CN: Design; CN: Design; Hold: Design; Hold: Design; CN: CN; Close: CN | Close | [5 empty] | 257000
FA | FC-107 |  | 1819 Building (HVAC, fire panel) | timing vendor's action | [7 empty] | Planning | Planning |  | Hold | Hold | Hold | Hold | Hold | Hold | [6 empty] | 185000
FA |  |  | PW Shop Improvements (electrical panels, roof, cracked walls) | complete |  |  |  | CN: Planning; CN: Planning; CN: Planning; CN: CN; Hold: Close | [6 empty] | 90000
FA |  |  | PD Station (fire alarm) |  |  |  |  | CN: Planning; CN: Planning; CN: Planning; CN: Close | [6 empty] | 120000
FA |  |  | PD Evidence Building (fire alarm, security system panels) |  |  |  |  | CN: Planning; CN: Planning; CN: Planning; CN: Close | [6 empty] | 120000
FA |  |  | Visitor Information Center (electrical panel) | working with Facilities Team |  |  |  | CN: Close | [6 empty] | 44500
RUSS
FA |  |  | Municipal Service Campus | revised site plans and prelim cost estimates | [22 empty] | 11303000
FA | FC-101 |  | Museum | awaiting structural and electrical and cost estimate | [7 empty] | permitting | Design | Design | Design | Design | AD | CN | CN | [7 empty] | 3200000
GRANTS - ON HOLD
ST |  |  | SS4A - Planning grant for Local Road Safety Plan | Submitted
ST | CP-140S |  | South Lake Stevens Multi-Use Path Phase II | [23 empty] | 3650000
ST | TBD-18 |  | South Lake Stevens Multi-Use Path Phase III | [23 empty] | 3500000
SW | SW-108 |  | 36th St Culvert Replacement | [23 empty] | 1765000
FA | FC-204 |  | Police Training Center Lighting | [23 empty] | 50000
88087500
TOTAL
|  |  |  | Status Legend: | Good
Impeded
Stopped
|  |  |  | Phase Legend |  | Planning
Funding/Granting
Design
ROW
Advertisement
Construction
Closeout

## 2025
City of Lake Stevens | [29 empty] | 601785 | 326963 | 2045440 |  | 50158 | 3391282 |  |  |  | 280000
2025 Capital Improvement Projects
Project type. | CFP No. | Project Name | 2024 | 2025 |  |  |  | 2026 | Project Charter | Pre-app Done | Total Project Cost | 2024 Budget | 2024 Spent | Difference | 2025 Request | 2025 Additional Needed |  | 2026 | 2027 | 2028 | 2029 | 2030 | Grants |  |  | Gen | PR | Rental | Street | TIZ1 | TIZ2 | TIZ3 | TBP | FIL | PM | R1 | R2 | FC | SW | SWC | Cap
|  |  | Q4 | Q1 | Q2 | Q3 | Q4 | 2026 | [8 empty] | Barb's Finance Notes | [5 empty] | Amount | Source | Notes | 001 | 004 | 005 | 101 | 301 | 301 | 301 | 120 | 301 | 302 | 303 | 304 | 306 | 309 | 411 | other
ERIK | [41 empty] | 0 | 0
ST | TBD-02/03 | 91st Ave SE Sidewalk (4th to Market) & (8th to 4th St SE) | [8 empty] | 1690000 | 1854500 | 1690000 | 164500 | 0 | -164500 | Project Completion - TIB Grant Submission needed | [5 empty] | 442564 | TIB | TIB # C-P-146(002)-1 | [16 empty] | 0 | 0
PA | PR-107 | Lake Stevens Bayview Connector Phase 0 | [8 empty] | 1050000 | 1861301 | 1050000 | 811301 | 0 | -811301 | RF $800K for 1A | [24 empty] | 0 | 0
PA | PR-108 | Lake Stevens Bayview Connector Phase 0.5 | [8 empty] | 800000 | 0 | 0 | 0 | 800000 | 800000 | [10 empty] | 198000 | [7 empty] | 390000 |  | 212000 |  |  |  |  | 800000 | 0
PA | PR-100 | Frontier Heights Phase II | [8 empty] | 2400000 | 2268784 | 50000 | 2218784 | 2350000 | 131216 | Construction - RF | [5 empty] | 1204352 | RCO | Secured thru 2025 |  | 60000 | [7 empty] | 1700000 |  | 590000 |  |  |  |  | 2350000 | 0 | RF
ST | RD-101 | Main St. Improvements (16th St NE to 20th St NE) | [8 empty] | 4040000 | 4100000 | 220000 | 3880000 | 3820000 | -60000 | RF Current Budgets | [5 empty] | 3304000 | FHWA | Obligate by June 2024 |  |  |  |  | 335000 |  |  | X |  |  |  | 3485000 |  |  |  |  | 3820000 | 0 | RF
ST | FC-112 | 131st Avenue Infrastructure Improvements | [8 empty] | 2800000 | 2047412 | 300000 | 1747412 | 2500000 | 752588 | RF Only - Sewer Dist $$? - No need to find $$ now | [5 empty] | 700000 | LSSD Share | Negotiations in process |  |  |  | X | 54000 |  | x |  | 46000 |  |  | 1520000 |  |  | 180000 | 700000 | 2500000 | 0
FA | FC-114 | Machias Sewer Infrastructure Improvements | [8 empty] | 3300000 | 200000 | 65000 | 135000 | 135000 | 0 | RF | 300000 | 300000 | 2500000 | [8 empty] | X | [7 empty] | 50000 |  |  | 85000 | X | 135000 | 0
BEN | [41 empty] | 0 | 0
ST | RD-203 | Annual Pavement Preservation Program | [8 empty] | 6460000 | 1000000 | 1060000 | -60000 | 900000 | 900000 | ST (Sewer UT), TBP, REET, | 900000 | 900000 | 900000 | 900000 | 900000 | [6 empty] | 200000 |  |  |  | 500000 |  |  |  | 200000 |  |  |  |  | 900000 | 0
SW |  | Downtown Regional Stormwater Facility | [8 empty] | 500000 | 0 | 75000 | -75000 | 425000 | 500000 | Design & Estimated Construction | [22 empty] | 425000 |  | 425000 | 0
ST | TBD-04 | 117th Ave NE Sidewalk (20th to 26th St NE) | [8 empty] | 1808000 | 308000 | 308000 | 0 | 300000 | 300000 | TBP - through final design | 1200000 | [11 empty] | 0 |  |  | 300000 | X |  |  | X |  | X | X |  | 300000 | 0
ST | TBD-07 | Soper Hill Sidewalk & Sewer Extension (Lake Drive to SR9) | [8 empty] | 3700000 | 0 | 0 | 0 | 400000 | 400000 | TBP - D&E | 300000 | 3000000 | [11 empty] | X |  | 400000 | X |  |  | X |  | X | X |  | 400000 | 0
SW | SW-104 | Bridge 06 Replacement - 36th Street NE | [8 empty] | 6661000 | 250000 | 30000 | 220000 | 1131000 | 911000 | PWTF Loan - Loan payments Budget (need amort) | 5500000 |  |  |  |  | 911000 | PW Board Loan | Award / unsecured | [14 empty] | 1131000 |  | 1131000 | 0
PA | PR-102 | Eagle Ridge Park Phase II | [8 empty] | 3459000 | 459000 | 120000 | 339000 | 339000 | 0 | RF - Pursuing grants |  | 3000000 |  |  |  | 2000000 | RCO | Applied / unsecured |  | 339000 | [9 empty] | X |  |  |  |  | 339000 | 0 | RF
WHITNEY | [41 empty] | 0 | 0
ST |  | Annual Citywide Road Striping and Thermoplastic | [8 empty] | 100000 | 100000 | 155000 | -55000 | 100000 | 100000 | Street | 100000 | 100000 | 100000 | 100000 | 100000 | [6 empty] | 100000 | [12 empty] | 100000 | 0
ST | RD-205 | Traffic Safety & Calming Program | [8 empty] | 650000 | 100000 | 50000 | 50000 | 100000 | 50000 | RF $50K = $100K | 100000 | 100000 | 100000 | 100000 | 100000 | [6 empty] | 100000 | [12 empty] | 100000 | 0
ST |  | EDDS Update
KIM | [41 empty] | 0 | 0
ST | RD-113 | 20th St NE and Main Street Roundabout | [8 empty] | 2700000 | 200000 | 200000 | 0 | 500000 | 500000 | $500K Local Needed?Construction to start late 2025. BA when grant obligated. | 2000000 |  |  |  |  | 2500000 | Federal Earmark | Obligate by Sept. 2026 |  |  |  |  | X |  |  | X |  |  |  | 500000 |  |  |  |  | 500000 | 0 | RF
ST | RD-202 | Annual ADA & Sidewalk Improvements | [8 empty] | 100000 | 150000 | 150000 | 0 | 100000 | 100000 | 309 - $50K for sidewalk & $50K ADA | 100000 | 100000 | 100000 | 100000 | 100000 | [14 empty] | X |  | 100000 |  |  | 100000 | 0
ST |  | Costco Closeout
SHANNON | [41 empty] | 0 | 0
SW | SW-106 | Hartford Crossing - New and Channel realignment | [8 empty] | 10600000 | 0 | 0 | 0 | 500000 | 500000 | Budget with Grant Revenue - BARS 3316600 | 500000 | 600000 | 9000000 |  |  | 500000 | EPA | Federal Direct Award / unsecured | [14 empty] | 500000 |  | 500000 | 0
SW | SW-111 | Catherine Creek/Hartford Crossing Replacement | [8 empty] | 3400000 | 0 | 0 | 0 | 280000 | 280000 | Design | 300000 | 2820000 | [20 empty] | 280000 |  | 280000 | 0
PARKS | [41 empty] | 0 | 0
PA | PR-206 | Eagle Ridge Property Acquisition | [8 empty] | 935000 | 10000 | 935000 | -925000 | 0 | 0 | Complete 2024 - PR - May come in under budget. | [24 empty] | 0 | 0
PA | PR-123 | Eagle Ridge Storage Building | [8 empty] | 25000 | 10000 | 2150 | 7850 | 22850 | 15000 | Updated per Sarah | [17 empty] | 22850 | [6 empty] | 22850 | 0
PA | PR-201 | N Cove Marina Feasibility & Marine Unit Relocation | [8 empty] | 4125000 | 160000 | 0 | 160000 | 160000 | 0 | RF | 850000 | 3115000 |  |  |  | $40000 $87000 | Fire District & Snohomish County | Secured | 54000 | [8 empty] | 106000 | X | [5 empty] | 160000 | 0
PA | PR-141 | North Cove Non-Motorized Dock | [8 empty] | 170000 | 0 | 170000 | -170000 | 0 | 0 | [25 empty] | 0 | 0
PA | PR-103 | North Cove Light Bollard Replacement | [8 empty] | 150000 | 0 | 0 | 0 | 150000 | 150000 | [18 empty] | 150000 | [6 empty] | 150000 | 0
PA | PR-104 | Cedarwood Property | [8 empty] | 1650000 | 500000 | 500 | 499500 | 499500 | 0 | RF for feasibility only - Not budgeting construction or grants until they approve scope change. | 1150000 |  |  |  |  | 1123000 | State | Secured | [9 empty] | 499500 | [6 empty] | 499500 | 0
PA | PR-113 | Davies Beach Pier Resurfacing | [8 empty] | 100000 | 0 | 0 | 0 | 100000 | 100000 | [18 empty] | 100000 | [6 empty] | 100000 | 0
PA | PR-106 | West Lake Park Recreation Amenities | [8 empty] | 100000 | 0 | 0 | 0 | 100000 | 100000 | [6 empty] | 100000 | Snohomish County | Secured | [9 empty] | 100000 | [6 empty] | 100000 | 0
PA | PR-203 | Lake Stevens Bayview Connector Phase 1 | [8 empty] | 2700000 | 0 | 0 | 0 | 500000 | 500000 | Design - Cost Sharing with Marysville |  | 2200000 | [15 empty] | 200000 |  | 300000 |  |  |  |  | 500000 | 0
Public Works O&M | [41 empty] | 0 | 0
FA | FC-111 | PW/Parks Building Feasibility Study | [8 empty] | 30000 | 30000 | 0 | 30000 | 30000 | 0 | RF | [11 empty] | 15000 | [10 empty] | 15000 |  | 30000 | 0
FA |  | Evergreen Office Building (siding, HVAC, fire alarm) | [8 empty] | 257000 | 0 | 0 | 0 | 257000 | 257000 | [11 empty] | 257000 | [13 empty] | 257000 | 0
FA | FC-107 | 1819 Building (HVAC, fire panel) | [8 empty] | 185000 | 100000 | 20000 | 80000 | 165000 | 85000 | [11 empty] | 65000 | [9 empty] | 100000 |  |  |  | 165000 | 0
FA |  | PW Shop Improvements (electrical panels, roof, cracked walls) | [8 empty] | 90000 | 0 | 0 | 0 | 90000 | 90000 | [21 empty] | 90000 |  |  |  | 90000 | 0
FA |  | PD Station (fire alarm) | [8 empty] | 120000 | 0 | 0 | 0 | 120000 | 120000 | [21 empty] | 120000 |  |  |  | 120000 | 0
FA |  | PD Evidence Building (fire alarm, security system panels) | [8 empty] | 120000 | 0 | 0 | 0 | 120000 | 120000 | [21 empty] | 120000 |  |  |  | 120000 | 0
FA |  | Visitor Information Center (electrical panel) | [8 empty] | 44500 | 0 | 0 | 0 | 8500 | 8500 |  |  | 36000 | [18 empty] | 8500 |  |  |  | 8500 | 0
PLANNING & CD | [41 empty] | 0 | 0
FA |  | Municipal Service Campus | [8 empty] | 11303000 | 11900000 | 7203000 | 4697000 | 4100000 | -597000 | RF - $11.8M budget per Russ (+$100K retainage) | [20 empty] | 4100000 |  |  |  | 4100000 | 0
FA | FC-101 | Museum | [8 empty] | 3200000 | 3200000 | 213000 | 2987000 | 2987000 | 0 | RF | [5 empty] | 764000 | Capital Heritage Grant | Secured through 2025 |  | 680700 | [10 empty] | 2306300 |  |  |  | 2987000 | 0
GRANTS - ON HOLD | [41 empty] | 0 | 0
ST | TBD-05 | 91st Ave SE Sidewalk (20th to 12th St SE) | [8 empty] | 2600000 | 0 | 0 | 0 | 300000 | 300000 | Planning D&E. Hold for grant - Do not budget | 300000 | 2000000 |  |  |  | 800000 | WSDOT SRTS | Applied / unsecured | [6 empty] | X | X | X |  |  | X |  | X | X |  | 0 | 300000
ST |  | 20th St SE Widening, Trestle to 83rd Ave | [8 empty] | 14200000 | 0 | 0 | 0 | 200000 | 200000 | Local Match? Hold for Grant - Do not budget | 1500000 | 1500000 | 11000000 |  |  | 2432000 | TIB | Applied / unsecured | [16 empty] | 0 | 200000
ST | CP-140S | South Lake Stevens Multi-Use Path Phase II | [8 empty] | 3650000 | 0 | 0 | 0 | 0 | 0 |  |  | 400000 | 250000 | 3000000 |  | 3000000 | Capital Transportation | Available 2029 | [6 empty] | X |  |  |  |  | X |  | X | X |  | 0 | 0
ST | TBD-18 | South Lake Stevens Multi-Use Path Phase III | [8 empty] | 3500000 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 500000 | 3000000 | [9 empty] | X | X | X |  |  | X |  | X | X |  | 0 | 0
SW | SW-108 | 36th St Culvert Replacement | [8 empty] | 1765000 |  | 0 | 0 | 265000 | 265000 | Hold for grant. $40K Local |  | 1500000 |  |  |  | 225000 | Fish Barrier Removal | Applied / unsecured | [14 empty] | X | X | 0 | 265000
FA | FC-204 | Police Training Center Lighting | [8 empty] | 50000 | 0 | 0 | 0 | 50000 | 50000 | Hold for grant. Do not Budget | [6 empty] | Energy Conservation | [17 empty] | 0 | 50000
[11 empty] | 107287500 | 30808997 | 14066650 | 16742347 | 24904850 | 6952503 | 0 | 15100000 | 21671000 | 23950000 | 4700000 | 4200000 | 20005916
[11 empty] | TOTAL | 2024 Budget | 2024 Spent | Difference | 2025 Request | 2025 Additional Needed |  | 2026 | 2027 | 2028 | 2029 | 2030
17952347
Other 2024 CIP
| RD-106 | 79th Ave SE & 8th St SE Intersection Improvements | [9 empty] | 135000 | 55000 | 80000 | 0 | -80000
| RD-201 | Wayfinding Signage | [9 empty] | 100000 | ?? | #VALUE! | 0 | #VALUE!
| SW-201 | Hartford Property Acquisition and Restoration | [9 empty] | 523975 | ?? | #VALUE! | 0 | #VALUE!
Note on AN3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sidewalk
Note on AO3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stormwater Capital
Note on AP3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Other Capital
Note on N6: Kim Klinkers: Check that TIB grant for $442k is accounted for.
Note on X11: Kim Klinkers: Estimate. Working through DEA.
Note on R15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kim was this feasibility, design & engineering only? Reply: It should be design and construction. I guessed at the construction cost for now. It will need to be refined once we are in the design phase. Reply: Okay
Note on P25: Kim Klinkers: Need ~ $500k local funds for design and federal match req.
Note on P33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Roll Over Unspent from last year and add a new $15k
Note on P53: Kim Klinkers: Waiting for WSDOT grant notice.
Note on P54: Kim Klinkers: Waiting for TIB grant notice.

## 2024
|  | Status: | 2024-10-14 |  |  |  | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
Project Name | Project Type | PM | Budget | Schedule | Scope | Status | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Main Street Improvements (16th to 20th) | Streets | Erik |  |  |  | Bid open 10/15
2024 Pavement Preservation | Streets | Erik |  |  |  | Started 8/12
91st Ave Sidewalk, 4th St to Market | Streets | Erik |  |  |  | Started 8/12
91st Ave Sidewalk, 8th St to 4th St | Streets | Erik |  |  |  | Started 8/12
Frontier Heights Park Phase II | Park | Erik |  |  |  | Process change request
LS Bayview Connector Phase 0 (Powerline Trail) | Park | Erik |  |  |  | Started 7/29
131st Ave Infrastructure Improvements | Fac/Util | Erik |  |  |  | Final design, ROW
Machias Lift Station | Fac/Util | Erik |  |  |  | Design report in/pending comments
117th Ave Sidewalk, 20th St to 26th St | Streets | Ben |  |  |  | Kickoff design
Main Street/20th Street Roundabout | Streets | Ben |  |  |  | Pre-app meeting
Regional Stormwater Facility | Storm | Kim |  |  |  | Prelim. scoping
ADA Transition Plan | Streets | Kim |  |  |  | Final draft
Weir Replacement | Storm | Shannon |  |  |  | Prelim. design
36th Street Bridge Replacement | Storm | Shannon |  |  |  | Loan request
Annual Striping Program | Streets | Whitney |  |  |  | Complete
79th Ave & 8th St Intersection | Streets | Whitney |  |  |  | Complete
EDDS Update | Streets | Whitney |  |  |  | Underway
91st Ave Sidewalk, 20th St to 12th St | Streets
North Lakeshore Dr., Main Street to 123rd Ave NE | Streets
Soper Hill Rd. SR9 to Lake Dr | Streets
Wayfinding Signage | Streets | P&CD
91st Ave NE Commercial Revitalization Phase I | Streets | P&CD |  |  |  | Prelim. design done
Eagle Ridge Park Phase II | Park | Parks |  |  |  | Grant applications
N Cove Marina Feasibility & Marine Unit Relocation | Park | Parks
N Cove Row Dock | Park | Parks |  |  |  | Design & permitting
Cedarwood Community Center | Park | Parks |  |  |  | Remove?
Eagle Ridge Property Acquisition | Park | Parks
PW Shop Building Feasibility/Preliminary Design | Fac/Util | PW
Security Cameras | Fac/Util | IT
Museum | Fac/Util | P&CD
City Hall Purchase and Tenant Improvement | Fac/Util | P&CD
1819 Commercial Building Paint and Remodel | Fac/Util | PW
|  | On track | [18 empty] | Scoping/Pre-design Stage
|  | Impeded | [18 empty] | Design/Permitting Stage (Starts with Executing Design Contract(s)
|  | Obstructed | [18 empty] | ROW Acquisition/Temporary Construction Access (Design Slowdown)
|  | Celebrate | [18 empty] | External Agency Permitting (Design Slowdown)
Invitation for Bids Window
Construction Stage (Starts with Award Date; excludes close-out)
Schedule Adjust from Previous Meeting
.

## 2023.1
2023 Capital Work Plan - City of Lake Stevens
| Original Date: 2/17/2023 |  | Date Prepared: |  | 2023-08-07
|  |  | Prepared By: |  | Erik Mangold
| Project | Project Manager | Start Date | Duration | End Date
1 | Main Street & 20th Street RAB | Aaron | 2023-05-01 | 183 | 2023-10-31
2 | Law Enforcement Dock | Aaron | 2023-06-01 | 213 | 2023-12-31
3 | 131st Ave NE Sewer Extension | Aaron | 2023-05-01 | 183 | 2023-10-31
4 | Parks Relocation/Sewer Relocation | Aaron | 2023-08-01 | 152 | 2023-12-31
5 | Main Street | Erik | 2023-01-01 | 607 | 2024-08-30
6 | South Lake Stevens MUP II & III | Erik | 2023-01-01 | 90 | 2023-04-01
7 | Mill Spur Parking Lot | Erik | 2023-04-01 | 95 | 2023-07-05
8 | Gateway Sign @ S. lake Stevens Rd | Erik | 2023-03-01 | 155 | 2023-08-03
9 | Gateway Signs @ SR204 | Erik | 2023-08-04 | 50 | 2023-09-23
10 | Frontier Heights Park Phase II | Erik | 2023-01-01 | 700 | 2024-12-01
11 | Sunset Park Dock | Erik | 2023-01-01 | 272 | 2023-09-30
12 | Sunset Park Improvements | Erik | 2023-01-01 | 290 | 2023-10-18
13 | Eagle Ridge Park Phase II | Erik | 2023-08-07 | 365 | 2024-08-06
14 | Powerline Trail | Erik | 2023-06-01 | 365 | 2024-05-31
15 | Festival Street Restroom | Erik | 2023-08-15 | 90 | 2023-11-13
16 | ADA Transition Plan | Kim | 2023-01-01 | 364 | 2023-12-31
17 | Annual Striping Program | Kim | 2023-08-01 | 60 | 2023-09-30
18 | Annual Pavement Preservation Program | Kim | 2023-10-01 | 457 | 2024-12-31
19 | 91st Ave Sidewalk, 4th St to Market | Frank | 2023-08-01 | 244 | 2024-04-01
20 | 91st Ave Sidewalk, 8th St to 4th St | Frank | 2023-08-01 | 244 | 2024-04-01
21 | 91st Ave Sidewalk, 20th St to 12th St | Frank | 2023-08-01 | 244 | 2024-04-01
22 | 117th Ave Sidewalk, 20th St to 26th St | Frank | 2023-08-01 | 244 | 2024-04-01
23 | 36th Street Culvert Replacement | Shannon | 2023-01-01 | 700 | 2024-12-01
34 | Weir Replacement | Shannon | 2023-01-02 | 700 | 2024-12-02
25 | Traffic Calming | Whitney | 2023-01-01 | 364 | 2023-12-31
26 | 79th Ave SE/8th St. SE Intersection | Whitney | 2023-07-01 | 138 | 2023-11-16
27 | ADA Ramp Improvements | Whitney | 2023-01-01 | 256 | 2023-09-14
28 | North Cove Water Feature | Whitney | 2023-04-01 | 60 | 2023-05-31
Guiding Principles
1. Engineering Division Manages Projects
2. Charter is gatekeeper to advance from initiation, must be budgeted, must assign PM
3. Project Managers do not manage more than 4 projects. Number of projects by employee are below
Erik Mangold = 4
Frank = 4
Kim Klinkers = 2
Shannon Farrant = 2
Whitney Ojalehto = 2
Aaron Halverson = 2
Approved by
Kim Klinkers, City Engineer
Approved by
Aaron Halverson, Public Works Director
Approved by
Gene Brazel, City Administrator
January 1st
|  | February 1st | 31
|  | March 1st | 28
|  | April 1st | 31
30
31
30
31
Formulas:
End Date = [Start Date]+[Duration]

## 2023
2023 Capital Work Plan - City of Lake Stevens
| Original Date: 2/17/2023 |  | Date Prepared: |  | 2023-07-10
|  |  | Prepared By: |  | Erik Mangold
| Project | Project Manager | Start Date | Duration | End Date
1 | Main Street & 20th Street RAB (Pre-Design) | Aaron | 2023-05-01 | 183 | 2023-10-31
| Law Enforcement Dock (Pre-design) | Aaron | 2023-06-01 | 213 | 2023-12-31
2 | 131st Ave NE Sewer Extension (Design) | Aaron | 2023-05-01 | 183 | 2023-10-31
3 | Parks Relocation/Sewer Relocation | Aaron | 2023-08-01 | 152 | 2023-12-31
| Main Street (Design) | Erik | 2023-01-01 | 424 | 2024-02-29
4 | Main Street (Construction) | Erik | 2024-03-01 | 183 | 2024-08-31
5 | South Lake Stevens MUP II & III (Pre-Design) | Erik | 2023-01-01 | 90 | 2023-04-01
6 | Mill Spur Parking Lot (Design) | Erik | 2023-04-01 | 40 | 2023-05-11
7 | Mill Spur Parking Lot (Construction) | Erik | 2023-05-12 | 49 | 2023-06-30
| Gateway Sign (Construction) | Erik | 2023-03-01 | 153 | 2023-08-01
8 | Frontier Heights Park Phase II (Design) | Erik | 2023-01-01 | 460 | 2024-04-05
9 | Frontier Heights Park Phase II (Construction) | Erik | 2024-04-05 | 240 | 2024-12-01
10 | Sunset Park Dock & Shoreline (Design) | Erik | 2023-01-01 | 177 | 2023-06-27
11 | Sunset Park Dock & Shoreline (Construction) | Erik | 2023-06-28 | 95 | 2023-10-01
12 | Sunset Park Improvements (Design) | Erik | 2023-01-01 | 200 | 2023-07-20
13 | Sunset Park Improvements (Construction) | Erik | 2023-07-06 | 90 | 2023-10-04
14 | Eagle Ridge Park Phase II (Design) | Erik | 2023-05-01 | 365 | 2024-04-30
15 | Eagle Ridge Park Phase II (Construction) | Erik | 2024-05-01 | 180 | 2024-10-28
16 | Powerline Trail (Design) | Erik | 2023-06-01 | 245 | 2024-02-01
| Powerline Trail (Construction) | Erik | 2024-03-15 | 120 | 2024-07-13
17 | Festival Street Restroom (Construction) | Erik | 2023-08-15 | 90 | 2023-11-13
18 | ADA Transition Plan | Kim | 2023-01-01 | 364 | 2023-12-31
| Annual Striping Program | Kim | 2023-07-17 | 60 | 2023-09-15
19 | Annual Pavement Preservation Program | Kim | 2023-10-01 | 457 | 2024-12-31
| 91st Ave Sidewalk, 4th St to Market (Design) | Senior Engineer | 2023-08-01 | 244 | 2024-04-01
20 | 91st Ave Sidewalk, 8th St to 4th St (Design) | Senior Engineer | 2023-08-01 | 244 | 2024-04-01
| 91st Ave Sidewalk, 20th St to 12th St (Design) | Senior Engineer | 2023-08-01 | 244 | 2024-04-01
21 | 117th Ave Sidewalk, 20th St to 26th St (Design) | Senior Engineer | 2023-08-01 | 244 | 2024-04-01
22 | 36th Street Culvert Replacement (Design) | Shannon | 2023-01-01 | 700 | 2024-12-01
23 | Weir Replacement (Design) | Shannon | 2023-01-02 | 700 | 2024-12-02
| Traffic Calming | Whitney | 2023-01-01 | 364 | 2023-12-31
24 | 79th Ave SE/8th St. SE Intersection (Design) | Whitney | 2023-05-15 | 138 | 2023-09-30
25 | ADA Ramp Improvements (Design) | Whitney | 2023-01-01 | 155 | 2023-06-05
26 | ADA Ramp Improvements (Construction) | Whitney | 2023-06-06 | 101 | 2023-09-15
27 | North Cove Water Feature (Construction) | Whitney | 2023-04-01 | 60 | 2023-05-31
Guiding Principles
1. Engineering Division Manages Projects
2. Charter is gatekeeper to advance from initiation, must be budgeted, must assign PM
3. Project Managers do not manage more than 4 projects. Number of projects by employee are below
Erik Mangold = 4
Senior Engineer = 4
Kim Klinkers = 2
Shannon Farrant = 2
Whitney Ojalehto = 2
Aaron Halverson = 2
Approved by
Kim Klinkers, City Engineer
Approved by
Aaron Halverson, Public Works Director
Approved by
Gene Brazel, City Administrator
January 1st
|  | February 1st | 31
|  | March 1st | 28
|  | April 1st | 31
30
31
30
31
Formulas:
End Date = [Start Date]+[Duration]